## Scorecard
The programme against OBJ-01 to OBJ-08, as set in the charter of 2026-01-19
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 09 · Illustrative Portfolio Sample
ID | Target | Actual | Verdict
OBJ-01 | Unmodified opinion, form of opinion in Section I | Unmodified, 2027-02-26 | Met
OBJ-02 | ISO/IEC 27001:2022 certificate issued by 2027-01-31 | Issued 2027-01-22 | Met
OBJ-03 | ≥ 70% of evidence artefacts serving both deliverables | 16.9% — 356 of 2,103 | Missed
OBJ-04 | ML-1, ML-2 and ML-3 closed and verified, 3 of 3 by 2026-06-30 | 3 of 3 closed and verified | Met
OBJ-05 | Mean questionnaire turnaround from 11.4 days to ≤ 3.0 days | 2.6 days across 47 questionnaires, Q1 2027 | Met
OBJ-06 | Register maintained; quarterly review cadence, no lapse | Five CAL-06 occurrences, no lapse | Met
OBJ-07 | Committed spend ≤ $1,400,000 | $1,366,000 | Met
OBJ-08 | Awareness training completion ≥ 95% of 187 staff | 96.8% — 181 of 187 | Met
Seven met, one missed — and the missed one is the integration objective the programme was designed around.
OBJ-03 asked for 70% of evidence ARTEFACTS to serve both deliverables. The actual is 356 of 2,103 — 16.9%, a miss by a factor of four.
The measure was wrong. Most evidence is framework-specific: a clause 9.2 audit plan is not a SOC 2 artefact and a Section IV test population is not an ISO one.
The dividend is in the 113 of 150 controls that serve both frameworks — 75.3%, which clears the 70% bar on the measure the objective should have used.
OBJ-03 is missed on what it said and met on what it meant, and both halves of that sentence are findings.
The better measure was identified in Phase 08 by an adversarial reader, not by the people who wrote the objective.