## Band arithmetic
The published close forecast against the actual close position
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 09 · Illustrative Portfolio Sample
Band | Forecast (Phase 03, ADR-0015) | Actual (2026-12-29) | Difference
High | 0 | 0 | 0
Moderate | 16 | 17 | 1
Low | 22 | 21 | -1
Total | 38 | 38 | 0

## The five entries
One band, five entries — and they diverge in both directions
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 09 · Illustrative Portfolio Sample
Entry | Forecast | Actual | Direction | Why
R-08 | 2 × 3 = 6, Low | 3 × 3 = 9, Moderate | UP — Moderate where Low was forecast | Raised to 5 × 3 = 15 in September on nine occurrences of its described event in ninety-two days, and brought back two steps and not three: six weeks of CA-06-03's corrected emergency change path is not a window, and DEC-810 is the risk owner refusing the rating that would have suited the register
R-09 | 2 × 3 = 6, Low | 4 × 3 = 12, Moderate | UP — Moderate where Low was forecast | Its described event occurred — access provisioned ahead of recorded manager approval in 2 of the window's 40 provisioning requests, tested in full, which is exception 8. The entry did not move at all
R-18 | 2 × 3 = 6, Low | 3 × 3 = 9, Moderate | UP — Moderate where Low was forecast | Its described event occurred, on 2026-09-08: a 71-minute Severity-1 and SC-01 missed in September for the 599 customers served from us-east-1
R-13 | 3 × 3 = 9, Moderate | 2 × 3 = 6, Low | DOWN — Low where Moderate was forecast | The control changed — CNB-C-032 now requires a phishing-resistant factor on every path reaching production — and the window tested it. The forecast reasoned about what a successful phish yields; the review found the control had changed the path instead
R-14 | 3 × 3 = 9, Moderate | 2 × 3 = 6, Low | DOWN — Low where Moderate was forecast | CUEC-05's outreach and the window's export record — specifically CNB-C-111's band check, CloudNimbus's own preventive control sitting in front of the customer step. GOV-32 records it as the weakest of the nineteen movements
Three up, two down, net one. 16 + 3 - 2 = 17; 22 - 3 + 2 = 21.
A forecast right at the band level and wrong five times underneath it is not a good forecast that got lucky, and it is not a bad one.
The band count is an aggregate, and aggregates hide compensating errors: the total absorbed four of the five.
A programme that checked only the aggregate would have declared the forecast a success and learned nothing from the five.
ADR-0015 required the forecast to be published in the first place. A forecast nobody publishes is a forecast nobody can be wrong about.

## The register's life
Every change to the register between the baseline and the close
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 09 · Illustrative Portfolio Sample
Date | Event | Position after
2026-04-10 | Baseline published at MS-04 — 36 entries | 7 High · 17 Moderate · 12 Low = 36
2026-05-22 | R-37 admitted on penetration test evidence at 4 x 5 = 20 | 8 · 17 · 12 = 37
2026-06-15 | CAL-06: R-37 re-rated to 2 x 5 = 10 — the first review of a register | 7 · 18 · 12 = 37
2026-09-29 | CAL-06: six reductions proposed, none accepted; R-08 raised to 5 x 3 = 15 unproposed | 8 · 17 · 12 = 37
2026-10-23 | R-38 admitted between reviews under DEC-306 at 3 x 4 = 12 | 8 · 18 · 12 = 38
2026-10-28 | R-24 re-rated upward 2 x 4 = 8 to 3 x 4 = 12, without crossing a band | 8 · 18 · 12 = 38
2026-12-29 | CAL-06: 19 moved, 7 held, 12 unchanged — the only large movement in the register's life | 0 · 17 · 21 = 38
2027-03-09 | CAL-06: all thirty-eight held. The first review of a new cycle has nothing to move on | 0 · 17 · 21 = 38
Nothing was closed and nothing was removed, at any point. Thirty-six entries have been on the register since 2026-04-10 and two were added on evidence.