## The programme
CloudNimbus, Inc. — the programme in figures, 2026-01-19 to 2027-03-11
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 09 · Illustrative Portfolio Sample
Item | Value | Note
Phases issued | 9 | Phase 01 re-issued once, Phase 02 once, Phase 04 three times
Controls in the library | 150 | 113 serve both frameworks, 21 are SOC 2-only and 16 are ISO-only; two were added mid-programme, on evidence
Trust services criteria in scope | 61 | CC 33 · A1 3 · PI1 5 · C1 2 · P 18
Annex A controls | 93 | 91 determined necessary, 2 excluded — A.7.11 and A.7.12
Register entries | 38 | 36 at baseline, 2 added on evidence, none closed and none removed
Register at close | 0 High · 17 Moderate · 21 Low | Against a published forecast of 0 · 16 · 22
Decisions | 116 | DEC-101 to DEC-915
Architectural decision records | 45 | ADR-0001 to ADR-0045
Governance records | 36 | GOV-01 to GOV-36
Evidence artefacts | 2103 | 1,847 for the examination, 612 for the certification audit, 356 for both
Programme cost | $1,366,000 | Against a board-approved envelope of $1,400,000 — $34,000, or 2.4%
Effort | 4.6 FTE | Across a 187-person organisation with 8 people in Security
Test exceptions | 9 | Under 9 of the 61 criteria; 52 carry none
ISO findings at Stage 2 | 1 major · 4 minor · 7 opportunities | The major was raised 2026-12-02 and verified closed 2027-01-15 — forty-four days
Adversarial review findings | 338 | 19, 29, 26, 33, 34, 74, 77 and 46 across the eight phases issued before this one

## Obligations
The twelve contractual and certification obligations at 2027-03-11
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 09 · Illustrative Portfolio Sample
ID | Column 2 | Column 3 | Column 4
O1 | Maintain a current SOC 2 Type II report covering at least Security, Availability and Confidentiality, available under non-disclosure on request, to all 640 | Annual | Met for the first time. The report of 2027-02-26 covers all five categories. 37 of the 522 non-enterprise customers requested it and 37 were delivered
O2 | Provide the report to each of the 118 enterprise-tier customers within thirty days of issuance | Within 30 days of issuance | Discharged. 118 delivered by 2027-03-06 against a deadline of 2027-03-28
O3 | Provide a bridge letter covering the gap between the report period end and the customer's fiscal year end, on request | On request | Discharged for nine requests; two open. Nine letters issued 2027-03-01 to 2027-03-10; two requests await gap periods that have not ended
O4 | Notify the customer of a security incident affecting its data within forty-eight hours of determination | Within 48 hours | Never engaged, and tested once. 0 security incidents determined in the window from 10,336 alerts. The RT-02 condition was assessed against it and recorded not engaged
O5 | Maintain a current sub-processor list; give thirty days' notice of a new sub-processor with a right to object | 30 days before engagement | Engaged once and met. Notice issued 2026-10-02 for a replacement outbound email delivery sub-processor effective 2026-11-05 — thirty-four days
O6 | Assist the customer with a data subject request within ten business days | Within 10 business days | Engaged 58 times and missed once. One assembly took twelve business days; it is exception 7 in Section IV and CA-07-05 is open
O7 | Delete or return customer data within thirty days of termination and certify completion | Within 30 days of termination | Engaged nine times and met nine times. Mean eleven days to certificate, longest nineteen, none late
O8 | Keep personal data at rest within eu-central-1 for the 41 residency customers | Continuous | Held at every instant of the window and since. The only continuous obligation in the register, and the most expensive one
O9 | Report a material security incident to the board within five business days | Within 5 business days | Never engaged. INC-2026-031 was an availability incident with no security characterisation. Recorded as not engaged at the management review of 2026-09-30
O10 | Notify the certification body of significant changes to the ISMS, its scope or the organisation within thirty days | Within 30 days of the change | Engaged once and met. The ISMS scope statement reissued 2026-10-28 and Northgate notified inside the thirty days
O11 | Undergo a surveillance audit within twelve months of the certification decision | Annual | Not yet due. Certification decision 2027-01-20; the audit is scheduled for 2027-11. A plan, not an outcome
O12 | Provide management's written assertion and a representation letter at the conclusion of the examination | At each examination | Discharged for this examination. Both dated 2027-02-26