## Q4 to date
Quarter four to date — 2026-10-01 to 2026-11-27, 58 days
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 07 · Illustrative Portfolio Sample
Measure | October | November to the 27th | Period
Days | 31 | 27 | 58
Changes deployed | 54 | 43 | 97
— of which emergency | 2 | 1 | 3
Alerts triaged | 1904 | 1588 | 3492
— high-severity, all triaged inside thirty minutes | 66 | 55 | 121
Severity-1 or Severity-2 incidents | 0 | 0 | 0
Security incidents | 0 | 0 | 0
November is not a month until it closes, and this record gives no November availability figure. October: us-east-1 99.96% from 17 minutes; eu-central-1 100%.

## Deviations
Deviations and the one commitment failure
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 07 · Illustrative Portfolio Sample
ID | Control | Deviation | Population | Clause 10.2 | Kind
D-07-01 | CNB-C-126, CNB-C-127 | RT-02's generated job matched no rows for 68 consecutive nights after the 2026-08-17 partitioning of the eu-central-1 table, reporting success each night; 1,847,206 geolocation capture points were retained past their 13-month rule | 68 of 68 nights on 1 of 8 rules in 1 of 3 regions | Yes — CA-07-02 | Control deviation
D-07-02 | CNB-C-092 | One Tier 1 vendor held no current assurance artefact at two consecutive quarterly refreshes, 2026-07-30 and 2026-10-07 | 2 of 24 | Yes — CA-07-03 | Control deviation
D-07-03 | CNB-C-129 | One data subject request assembled in twelve business days against ten | 1 of 31 | Yes — CA-07-05 | Control deviation
— | SC-09 | Assistance with a data subject request within ten business days: not met once. Management determined the failure was not significant for DC4 purposes and recorded the determination — ADR-0034 | 1 of 31 | — | Service commitment failure — NOT a control deviation

## Decisions
Decisions DEC-701 to DEC-715
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 07 · Illustrative Portfolio Sample
ID | Decision | Date | Owner
DEC-701 | Notice of the replacement email delivery sub-processor issued at thirty-four days against a thirty-day commitment | 2026-10-02 | Tobias Lund
DEC-702 | Tier recorded as an axis of the vendor register and not as its classification | 2026-10-07 | Tobias Lund
DEC-703 | The two unowned AWS complementary user entity controls assigned rather than deemed covered | 2026-10-23 | Wes Delacroix
DEC-704 | All 41 EU-residency customers notified of the RT-02 over-retention, with the dissent minuted | 2026-10-26 | Tobias Lund
DEC-705 | The catch-up deletion is not certified complete until the backup residue window expires | 2026-10-27 | Devon Ashby
DEC-706 | CNB-C-149 admitted to the control library mid-window; the library is 149 | 2026-10-28 | Karim Haddad
DEC-707 | R-38 admitted to the register between quarterly reviews under DEC-306 | 2026-10-23 | Devon Ashby
DEC-708 | R-06 held at 4 × 4 = 16; its described event did not occur | 2026-10-28 | Devon Ashby
DEC-709 | The objecting customer's platform email suppressed rather than the change deferred | 2026-10-30 | Ana-Sofia Cruz
DEC-710 | Halcyon's bridge letter accepted, with the two uncovered months recorded rather than waived | 2026-11-06 | Rahul Bhargava
DEC-711 | The SC-09 miss determined not to be a significant failure, and the determination written down | 2026-11-17 | Tobias Lund
DEC-712 | The published sub-processor list corrected and the currency check moved to the change itself | 2026-11-20 | Tobias Lund
DEC-713 | The rewrite of RT-02 as a monthly partition drop deferred to 2027-01, rather than change the shape of CNB-C-127's completion record inside the observation window | 2026-10-24 | Devon Ashby
DEC-714 | CNB-C-120 moved from its DEC-409 month of 2026-12 into November by its own owner, ahead of the reconciliation | 2026-11-02 | Tobias Lund
DEC-715 | R-24 re-rated from 2 × 4 = 8 to 3 × 4 = 12 on likelihood; the consequence and the band are unchanged | 2026-10-28 | Tobias Lund

## Register
The register at 2026-11-27 — one addition, one re-rating, no review
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 07 · Illustrative Portfolio Sample
Band | Entering the period | Movement | At the vantage
High | 8 | 0 | 8
Moderate | 17 | +1 (R-38 admitted); R-24 re-rated within band | 18
Low | 12 | 0 | 12
Total | 37 | 1 | 38
Two entries changed in the period: R-38 was admitted and R-24 was re-rated upward.
R-38 admitted 2026-10-23 at 3 x 4 = 12, Moderate. Owner Devon Ashby.
R-24 — geolocation retained or used beyond the purpose the individual was told about — moved from 2 x 4 = 8 to 3 x 4 = 12 on 2026-10-28 under DEC-715. Its described event occurred.
Both ratings are Moderate, so no band count moved. A movement that does not change a band is still a movement, and a register that only records band changes has stopped measuring.
The eight floor stopped R-24 moving down. Nothing stopped it moving up, and nobody had asked.
R-38: a retention or deletion job reports success while its predicate matches nothing, so the absence of deletion is indistinguishable from nothing being due.
R-38 is not R-06. R-06 describes a job that fails silently; this job succeeded.
R-06 held at 4 x 4 = 16 and tested upward: its described event did not occur.
Admitted between quarterly reviews under DEC-306. The Q4 CAL-06 review falls on 2026-12-29 and has not been held.
The register has grown twice in the programme: R-37 in May, R-38 in October. Both on an assumption disproved.