## Retention schedule
Retention schedule RT-01 to RT-08, and how each ran in the period
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 07 · Illustrative Portfolio Sample
Rule | Information | Retention | Position at 2026-11-27
RT-01 | Time and attendance records | Contract term plus 90 days | Ran nightly under CNB-C-126 in all three regions; completion records under CNB-C-127
RT-02 | Geolocation at clock-in (PD-05) | 13 months, irrespective of contract term | **RT-02 FAILED** — see the next sheet
RT-03 | Expense records and receipt images | Contract term plus 90 days | Ran nightly under CNB-C-126 in all three regions; completion records under CNB-C-127
RT-04 | Absence and leave records | Contract term plus 90 days | Ran nightly under CNB-C-126 in all three regions; completion records under CNB-C-127
RT-05 | Authentication and audit logs | 13 months queryable, then 7 years pseudonymised | Ran nightly under CNB-C-126 in all three regions; completion records under CNB-C-127
RT-06 | Support interaction records | 24 months | Ran nightly under CNB-C-126 in all three regions; completion records under CNB-C-127
RT-07 | Backups and snapshots | 35 days, rolling | Ran nightly under CNB-C-126 in all three regions; completion records under CNB-C-127
RT-08 | All customer data after termination | Deleted within 30 days, with a certificate | Ran nightly under CNB-C-126 in all three regions; completion records under CNB-C-127

## RT-02 failure
D-07-01 — RT-02 in eu-central-1, 2026-08-17 to 2026-10-23
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 07 · Illustrative Portfolio Sample
Item | Value
Migration deployed | 2026-08-17 — the geolocation capture table in eu-central-1 partitioned by month
Mechanism | The migration could not partition in place. It built a new partitioned relation, copied thirteen months of rows into it, TRUNCATED the original and swapped the names. CNB-C-126's generator resolves each rule to a physical object by an identifier recorded at generation time, and an object identifier survives a rename — so the job went on addressing the emptied original
Why nothing alerted | CNB-C-127 alerts on a job that does not report inside its window. The job reported: rows deleted, 0. It executed correctly against an empty table
Nights the job ran and deleted nothing | 68
Rules affected | 1 of 8 — RT-02 only, and only in eu-central-1
Records retained past the 13-month rule | 1847206
Oldest record at discovery | 13 months and 67 days — 68 nights inclusive is 67 elapsed days
Individuals whose records were affected | 58412
— of whom had left their employer during the 68 nights | 2106
Customers with affected records | 34
EU-residency customers with none (capture disabled) | 7
Total EU-residency customers notified 2026-10-26 | 41
Discovered | 2026-10-23, assembling the Q4 retention evidence sample for the service auditor
Job target corrected and redeployed | 2026-10-24
Partition-drop rewrite | Deferred to 2027-01 under DEC-713 — it would change the shape of CNB-C-127's completion record inside the window
Migration status elsewhere | Not yet applied to us-east-1 or us-west-2; scheduled 2027-01 behind the retention rule change record
Catch-up deletion run | 2026-10-25
Completion record verified | 2026-10-27
Backup residue window under CNB-C-128 | 35 days from 2026-10-25 — expires 2026-11-29, after this vantage
New control admitted | CNB-C-149 on 2026-10-28; the library is 149
Register | R-38 admitted 2026-10-23 at 3 x 4 = 12, Moderate; R-24 re-rated upward 2 x 4 = 8 to 3 x 4 = 12 on 2026-10-28, without crossing a band
DC4 | BOTH limbs. The first because CNB-C-127's alert condition could not detect the failure mode; the second because SR-08 — retention enforced by scheduled deletion jobs — was not achieved in eu-central-1 for 68 nights

## CNB-C-149
CNB-C-149 — admitted 2026-10-28, and what a mid-window control costs
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 07 · Illustrative Portfolio Sample
Item | Value
Statement | A retention job that reports success having deleted zero rows on a rule whose eligible population is non-zero raises an alert to the data platform owner, and the alert is dispositioned before the next run
Family / Type / Cadence | P / Detective / Daily
Owner | Devon Ashby
Policy | POL-07
Criteria | P4.2, P4.3
Annex A | A.8.10, A.8.16
Population in the observation window | 65 nights, 2026-10-28 to 2026-12-31
Run at this vantage | 31 nights, 0 alerts raised
Disclosure | A relevant change to the system during the period — DC9, which Phase 09 carries
The cost | The eligible-population half requires a second implementation of the rule, independent of the job that deletes it. ADR-0031 records the alternative that was rejected
The limit | It detects TOTAL non-deletion and not partial. A predicate reaching twelve of thirteen partitions deletes a non-zero number of rows and CNB-C-149 is silent
The concentration | Devon Ashby owns CNB-C-126, CNB-C-127, CNB-C-128, CNB-C-149, CA-07-02 and R-38, and CNB-C-149 alerts the owner where CNB-C-127 alerts the on-call engineer. Recorded rather than resolved