## Stage 2
ISO/IEC 27001:2022 Stage 2 — Northgate Certification Services, 2026-11-30 to 2026-12-04
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 08 · Illustrative Portfolio Sample
ID | Grade | Requirement | Finding | Status at 2027-02-05
MAJ-01 | MAJOR | Clauses 9.2.1 and 9.2.2 a), and A.5.22 | The internal audit of 2026-09-14 to 2026-09-25 covered the 93 Annex A controls in the Statement of Applicability — the 91 determined necessary against their implementation status and the 2 excluded against their justification — and did not cover clauses 4 to 10 or operations in eu-central-1. Clause 9.2.1 requires internal audits to provide information on whether the ISMS conforms to the organisation's own requirements AND to the requirements of the document; clause 9.2.2 a) requires the audit criteria and scope to be defined for each audit. CNB-C-146 states the programme is risk-weighted across clauses 4 to 10 and the Annex A controls determined necessary. The limitation was recorded in the auditor's own report at 1.3, presented to the management review of 2026-09-30 under input d) 3), and deferred. The same failure engages A.5.22, because the audit is a supplier service whose scope CloudNimbus set and never reviewed — and CNB-C-092, which reads Camberwell's assurance artefact quarterly, could not have caught it, because reading a supplier's artefact is not reviewing the scope you gave it. One nonconformity, not two | Correction and corrective action 2026-12-19; supplementary audit 2027-01-13; VERIFIED CLOSED 2027-01-15
MIN-01 | Minor | Clause 7.5.3 | Two further items of documented information past their review date — the same requirement Camberwell raised as NC-INT-01 in September and which was recorded closed on 2026-10-09. The closure fixed the items and not the mechanism | Corrective action open
MIN-02 | Minor | A.5.30, clause 8.1 | ICT readiness for business continuity: two of the four limbs are carried by no control in the library. This is Phase 06's IS-24, referred and not closed | Corrective action open; IS-24 closed by this finding
MIN-03 | Minor | A.8.16, clause 9.1 | The evaluation-methods gap Camberwell raised as NC-INT-02 remained open for four of the sixteen assurance calendar items | Corrective action open
MIN-04 | Minor | A.5.19, A.5.22 | One Tier 1 vendor held no current assurance artefact at two consecutive quarterly refreshes. This is Phase 07's D-07-02, found by CloudNimbus in July and again in October | Corrective action open
Plus 7 opportunities for improvement, OFI-01 to OFI-07. An opportunity for improvement is not a nonconformity and carries no obligation.

## All findings
Every finding raised against CloudNimbus in the assurance period
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 08 · Illustrative Portfolio Sample
ID | Source | Framework | Requirement | Status | Reported at
See logs/finding-log.md

## Stage 1
ISO Stage 1 — 2026-10-12 to 2026-10-14 · 0 nonconformities, 6 areas of concern
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 08 · Illustrative Portfolio Sample
ID | Area of concern | Would have escalated at Stage 2 | Closed
AOC-01 | The Statement of Applicability's status fields are stale — clause 6.1.3 d) requires the SoA to state whether each necessary control is implemented | YES | SoA reissued 2026-10-30
AOC-02 | The ISMS scope statement does not reflect the region-partitioned log archive or the sub-processor change then in notice — clause 4.3 | YES | Reissued 2026-10-28; Northgate notified inside 30 days under O10
AOC-03 | CNB-C-136's re-scheduled 2026-08 occurrence did not happen and carried no dated closure | No | CA-06-04 dated; occurrence performed 2026-12-08
AOC-04 | Competence records under clause 7.2 incomplete for two of the eight security staff | No | 2026-11-06
AOC-05 | The clause 4.2 interested-parties determination not reviewed since 2026-02 | No | 2026-11-13
AOC-06 | The Amd 1:2024 climate determination recorded in a decision log and not in the clause 4.1 documented information | No | Moved into the clause 4.1 record 2026-10-22
Stage 1 evaluates whether internal audits and management review are being planned and performed. It found a programme that existed, ran and reported. Stage 2 asks what it covered — ADR-0036.