## Close
The register at the December CAL-06 review, 2026-12-29
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 08 · Illustrative Portfolio Sample
Band | Entering | Leaving | Movement
High | 8 | 0 | -8
Moderate | 18 | 17 | -1
Low | 12 | 21 | 9
Total | 38 | 38 | 0
19 entries moved. 7 were held with a stated reason. 12 already-Low entries did not move. 19 + 7 + 12 = 38.
Six of the nineteen moved two likelihood steps and each was argued separately: R-01, R-05, R-08, R-10, R-13 and R-14.
R-08 moved two steps and not three. Six weeks of a corrected emergency change path is not a window.
The seven held: R-09 and R-18 because their described events occurred; R-19, R-20 and R-37 because likelihood 1 is reserved and no consequence changed; R-24 and R-38 because they were re-rated or admitted in October on their own events.
R-10 moved while the examination recorded an exception against the same control on the same day, about a different thing. A late revocation is not a late review.
Nothing was closed and nothing was removed, at this review or any other. Thirty-six entries have been on the register since 2026-04-10 and two were added on evidence.
Every earlier review said it was waiting for a population. The December review is the first at which the population exists.

## Decisions
Decisions DEC-801 to DEC-815
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 08 · Illustrative Portfolio Sample
ID | Decision | Date | Owner
DEC-801 | Camberwell's scope note read and agreed; clause coverage scheduled into the 2027 programme rather than 2026 | 2026-09-28 | Karim Haddad
DEC-802 | The scope note presented at the management review under input d) 3) and the deferral confirmed | 2026-09-30 | Elise Fontaine
DEC-803 | The Statement of Applicability reissued with current status fields | 2026-10-30 | Rahul Bhargava
DEC-804 | The ISMS scope statement reissued and Northgate notified under O10 | 2026-10-28 | Rahul Bhargava
DEC-805 | The PT2-03 export URL finding remediated ahead of the mobile release rather than in it | 2026-11-05 | Junia Okonkwo
DEC-806 | MAJ-01 accepted at the closing meeting without contest | 2026-12-04 | Karim Haddad
DEC-807 | The correction scoped as a full clause 4 to 10 and eu-central-1 audit rather than a documentation review | 2026-12-11 | Karim Haddad
DEC-808 | The audit programme document rewritten and a three-year coverage matrix adopted | 2026-12-18 | Karim Haddad
DEC-809 | The register review of 2026-12-29 moved nineteen entries, six of them by two steps | 2026-12-29 | Karim Haddad
DEC-810 | R-08 moved two steps and not three; six weeks of a corrected path is not a window | 2026-12-29 | Junia Okonkwo
DEC-811 | CNB-C-150 admitted after the observation window closed, and excluded from the examination | 2027-01-08 | Karim Haddad
DEC-812 | CNB-C-092 — the quarterly Tier 1 assurance refresh, which is the library's A.5.22 row — extended to carry an annual adequacy review of the scope CloudNimbus gives its audit supplier | 2027-01-08 | Tobias Lund
DEC-813 | The Stage 2 major disclosed in Section V, with the not-covered-by-the-opinion statement on its face | 2027-01-19 | Marisol Vega
DEC-814 | The certificate accepted and the first surveillance audit scheduled for 2027-11 | 2027-01-22 | Elise Fontaine
DEC-815 | The near-modification reported as open rather than predicted | 2027-02-03 | Rahul Bhargava