## Objectives
Programme Objectives — OBJ-01 to OBJ-08
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 01 · Illustrative Portfolio Sample
ID | Objective | Measure | Target | Owner
OBJ-01 | A SOC 2 Type II examination over all five trust services categories across a six-month period, on which the service auditor is able to express an unmodified opinion | Form of opinion in Section I | Unmodified | Karim Haddad
OBJ-02 | ISO/IEC 27001:2022 certification of the whole organisation by an ANAB-accredited certification body | Certificate issued | By 2027-01-31 | Karim Haddad
OBJ-03 | One control library and one evidence store serving both frameworks | Share of evidence artefacts serving both deliverables | ≥ 70% | Rahul Bhargava
OBJ-04 | Every matter carried from the 2025 Type I management letter closed before the observation window opens | ML-1, ML-2, ML-3 closed and verified | 3 of 3 by 2026-06-30 | Rahul Bhargava
OBJ-05 | Reduce the enterprise security-questionnaire burden on Sales and Customer Success | Mean days to return a completed questionnaire | 11.4 days → ≤ 3.0 days | Ana-Sofia Cruz
OBJ-06 | A risk assessment and treatment process meeting clause 6.1 and CC3.1–CC3.4, producing a maintained register | Register maintained; formal review cadence | Quarterly review, no lapse | Karim Haddad
OBJ-07 | Deliver within the approved envelope | Committed spend against $1,400,000 | ≤ $1,400,000 | Marisol Vega
OBJ-08 | Annual security awareness training completed across the organisation | Completion rate, 187 staff | ≥ 95% | Hannah Brill

## Budget
Programme Budget — B-01 to B-10
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 01 · Illustrative Portfolio Sample
ID | Line | Amount (USD)
B-01 | SOC 2 Type II examination — Ashcombe & Doyle LLP | 118000
B-02 | ISO 27001 certification — Northgate (Stage 1, Stage 2, first surveillance) | 47500
B-03 | Readiness advisory — Solstice Trust Advisors | 96000
B-04 | Outsourced ISMS internal audit — Camberwell Risk Partners | 34000
B-05 | Penetration testing — Ironwood Security Labs | 72000
B-06 | GRC and compliance-automation tooling | 88000
B-07 | Security tooling uplift — SIEM expansion, CSPM, DLP, SAST/DAST | 214000
B-08 | Internal labour (allocated) | 612000
B-09 | Training and awareness | 23000
B-10 | Contingency | 61500
| TOTAL COMMITTED | 1366000
| APPROVED ENVELOPE | 1400000
| HEADROOM | 34000

## Resourcing
Resourcing — 4.6 FTE-equivalents
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 01 · Illustrative Portfolio Sample
Function | FTE | Basis
VP Security & Trust — Karim Haddad | 0.6 | Programme ownership, ARC reporting, auditor relationship
Compliance Manager — Rahul Bhargava | 1 | Full-time programme management and evidence architecture
Engineering (Platform) — allocated | 1.1 | Control implementation across 63 microservices
Infrastructure & SRE — allocated | 0.9 | Availability, backup, DR, access review execution
Product (Calculation Engine) — allocated | 0.4 | Processing integrity control design and reconciliation
Data Platform — allocated | 0.3 | Retention, deletion and data lifecycle controls
Legal / DPO — allocated | 0.2 | DPAs, sub-processor assurance, privacy commitments
People — allocated | 0.1 | Screening, onboarding/offboarding, awareness training
Total | 4.6 | Against a 187-person organisation