## Milestones
Programme Milestones — MS-01 to MS-18
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 01 · Illustrative Portfolio Sample
ID | Milestone | Date | Phase
MS-01 | Board approves budget; programme kickoff | 2026-01-19 | 01
MS-02 | SOC 2 system scope and ISMS boundary defined | 2026-02-27 | 02
MS-03 | Asset inventory and data flows baselined | 2026-03-20 | 02
MS-04 | Risk assessment complete; baseline register published | 2026-04-10 | 03
MS-05 | Risk treatment plan and Statement of Applicability approved | 2026-04-24 | 03
MS-06 | Penetration testing complete | 2026-05-22 | 05
MS-07 | Unified control library published | 2026-06-05 | 04
MS-08 | Policy suite approved | 2026-06-12 | 04
MS-09 | ISMS declared operational | 2026-06-15 | 04
MS-10 | Type II observation window opens | 2026-07-01 | 05
MS-11 | Disaster recovery exercise complete | 2026-08-19 | 06
MS-12 | Clause 9.2 internal audit complete | 2026-09-25 | 08
MS-13 | Management review held | 2026-09-30 | 08
MS-14 | ISO Stage 1 complete | 2026-10-14 | 08
MS-15 | ISO Stage 2 complete | 2026-12-04 | 08
MS-16 | Type II observation window closes | 2026-12-31 | 08
MS-17 | ISO/IEC 27001:2022 certificate issued | 2027-01-22 | 09
MS-18 | SOC 2 Type II report issued | 2027-02-26 | 09