## RACI
Responsibility Matrix — A-01 to A-20
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 01 · Illustrative Portfolio Sample
ID | Activity | ARC | CEO | CFO | CTO | VP S&T | Compliance | Engineering | SRE | Legal/DPO | People
A-01 | Programme charter approval | A | R | C | C | R | C | I | I | C | I
A-02 | Budget approval and monitoring | C | C | A | I | R | C | I | I | I | I
A-03 | Trust services category selection | C | I | R | C | A | R | I | I | C | I
A-04 | ISMS scope determination (clause 4.3) | I | C | C | C | A | R | C | C | C | C
A-05 | SOC 2 system scope determination | I | I | C | R | A | R | C | C | C | I
A-06 | Information security policy issue (clause 5.2) | I | A | I | C | R | R | I | I | C | I
A-07 | Risk assessment and treatment (clause 6.1 / CC3) | C | I | C | C | A | R | C | C | C | C
A-08 | Statement of Applicability approval | I | I | I | C | A | R | C | C | C | I
A-09 | Unified control library design | I | I | I | C | A | R | C | C | C | C
A-10 | Policy suite drafting and approval | I | I | I | C | A | R | C | C | R | C
A-11 | Control implementation — technical | I | I | I | A | C | C | R | R | I | I
A-12 | Control implementation — people and process | I | I | I | I | A | R | C | C | C | R
A-13 | Evidence collection and retention | I | I | I | I | C | A | R | R | C | C
A-14 | Sub-processor and vendor assurance | I | I | C | I | C | R | I | I | A | I
A-15 | Security awareness training | I | I | I | I | C | C | I | I | C | A
A-16 | Internal audit programme (clause 9.2) | A | I | I | I | R | R | I | I | I | I
A-17 | Management review (clause 9.3) | C | A | C | C | R | R | C | C | C | C
A-18 | Nonconformity and corrective action (clause 10.2) | I | I | I | C | A | R | C | C | C | C
A-19 | Management's written assertion (SOC 2) | C | A | R | C | R | C | I | I | C | I
A-20 | Customer and board reporting | C | C | R | I | A | R | I | I | C | I

## Legend
RACI Legend and Convention
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 01 · Illustrative Portfolio Sample
Letter | Meaning | Note
R | Responsible | Performs the work. A row may carry more than one R.
A | Accountable | The single role that answers for the outcome. Exactly one per row.
C | Consulted | Two-way; input sought before the decision.
I | Informed | One-way; told after the decision.
Convention | RACI vs decision log | A RACI records accountability for the conduct of an activity. A decision log records who took a particular decision. Where they name different people both are correct: the RACI governs the work, the record governs the decision. See 01.08 section 4.1.