## Register
Risk Register Baseline — R-01 to R-36, with the published close forecast
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 03 · Illustrative Portfolio Sample
ID | Risk | Threat | Owner | L | I | Score | Band | Forecast L | Forecast I | Forecast score | Forecast band | Movement
R-01 | A defect in an authorisation or query path returns one tenant's compensation data to another | TH-05 | Junia Okonkwo | 4 | 5 | 20 | High | 2 | 5 | 10 | Moderate | L 4 → 2
R-02 | The calculation engine produces a wrong derived amount that reaches a payroll run undetected | TH-06 | Grete Lindqvist | 3 | 5 | 15 | High | 2 | 5 | 10 | Moderate | L 3 → 2
R-03 | A privileged CloudNimbus account is compromised and used to reach production | TH-02 | Wes Delacroix | 3 | 5 | 15 | High | 2 | 5 | 10 | Moderate | L 3 → 2
R-04 | Halcyon Identity becomes unavailable and no end user can authenticate | TH-09 | Wes Delacroix | 4 | 4 | 16 | High | 3 | 4 | 12 | Moderate | L 4 → 3
R-05 | Personal data of an EU-residency tenant leaves eu-central-1 through a log, backup or telemetry path | TH-07 | Devon Ashby | 4 | 4 | 16 | High | 2 | 4 | 8 | Moderate | L 4 → 2
R-06 | A scheduled retention or deletion job fails silently and data is kept past its rule | TH-08 | Devon Ashby | 4 | 4 | 16 | High | 2 | 4 | 8 | Moderate | L 4 → 2
R-07 | Production customer data reaches a non-production environment through an export or a bug-reproduction restore | TH-03 | Junia Okonkwo | 3 | 5 | 15 | High | 2 | 5 | 10 | Moderate | L 3 → 2
R-08 | A change is deployed to production without recorded peer review | TH-14 | Junia Okonkwo | 4 | 3 | 12 | Moderate | 2 | 3 | 6 | Low | L 4 → 2
R-09 | Access is provisioned before the manager approval that authorises it is recorded | TH-14 | Wes Delacroix | 4 | 3 | 12 | Moderate | 2 | 3 | 6 | Low | L 4 → 2
R-10 | A quarterly access review is completed late, or completed and not evidenced | TH-14 | Wes Delacroix | 4 | 3 | 12 | Moderate | 2 | 3 | 6 | Low | L 4 → 2
R-11 | A cloud resource is misconfigured and exposes data more widely than intended | TH-07 | Wes Delacroix | 3 | 4 | 12 | Moderate | 2 | 4 | 8 | Moderate | L 3 → 2
R-12 | A vulnerability in a third-party dependency is exploited before it is remediated | TH-04 | Junia Okonkwo | 3 | 4 | 12 | Moderate | 2 | 4 | 8 | Moderate | L 3 → 2
R-13 | An employee is successfully phished and their credentials or session are used | TH-12 | Karim Haddad | 4 | 3 | 12 | Moderate | 3 | 3 | 9 | Moderate | L 4 → 3
R-14 | A customer does not perform CUEC-05 and a wrong export reaches their payroll provider | TH-13 | Ana-Sofia Cruz | 4 | 3 | 12 | Moderate | 3 | 3 | 9 | Moderate | L 4 → 3
R-15 | Backup residue means data survives past the 30-day deletion commitment | TH-08 | Devon Ashby | 4 | 2 | 8 | Moderate | 2 | 2 | 4 | Low | L 4 → 2
R-16 | A vendor is misclassified in the register and its assurance obligations are not applied | TH-04 | Tobias Lund | 3 | 3 | 9 | Moderate | 2 | 3 | 6 | Low | L 3 → 2
R-17 | A sub-processor is engaged without the notice obligation O5 requires | TH-14 | Tobias Lund | 3 | 3 | 9 | Moderate | 2 | 3 | 6 | Low | L 3 → 2
R-18 | An availability incident breaches the 99.9% monthly commitment | TH-10 | Wes Delacroix | 3 | 3 | 9 | Moderate | 2 | 3 | 6 | Low | L 3 → 2
R-19 | Disaster recovery fails to meet the four-hour objective in a real event | TH-10 | Wes Delacroix | 2 | 5 | 10 | Moderate | 2 | 5 | 10 | Moderate | —
R-20 | eu-central-1 is lost, and obligation O8 forbids the cross-region recovery that would restore it | TH-10 | Wes Delacroix | 2 | 5 | 10 | Moderate | 2 | 5 | 10 | Moderate | —
R-21 | Audit and security logging is incomplete, so an event cannot be reconstructed | TH-14 | Karim Haddad | 3 | 3 | 9 | Moderate | 2 | 3 | 6 | Low | L 3 → 2
R-22 | A security incident is not notified to the affected customer within 48 hours | TH-14 | Karim Haddad | 3 | 3 | 9 | Moderate | 2 | 3 | 6 | Low | L 3 → 2
R-23 | A data subject request is not assisted within the 10 business days obligation O6 requires | TH-14 | Tobias Lund | 3 | 3 | 9 | Moderate | 2 | 3 | 6 | Low | L 3 → 2
R-24 | Geolocation is retained or used beyond the purpose the individual was told about | TH-14 | Tobias Lund | 2 | 4 | 8 | Moderate | 2 | 4 | 8 | Moderate | —
R-25 | The evidence architecture depends on one person | TH-14 | Marisol Vega | 3 | 2 | 6 | Low | 2 | 2 | 4 | Low | L 3 → 2
R-26 | An endpoint is lost or stolen with customer data cached on it | TH-11 | Wes Delacroix | 2 | 3 | 6 | Low | 2 | 3 | 6 | Low | —
R-27 | A leaver retains access after their last working day | TH-14 | Hannah Brill | 2 | 3 | 6 | Low | 2 | 3 | 6 | Low | —
R-28 | An unauthorised person obtains physical access to the Denver office | TH-01 | Hannah Brill | 2 | 2 | 4 | Low | 2 | 2 | 4 | Low | —
R-29 | A supplier ceases trading or withdraws a service at short notice | TH-09 | Tobias Lund | 2 | 3 | 6 | Low | 2 | 3 | 6 | Low | —
R-30 | Documented information becomes out of date and is relied on as current | TH-14 | Rahul Bhargava | 3 | 2 | 6 | Low | 2 | 2 | 4 | Low | L 3 → 2
R-31 | Awareness training completion falls below the 95% bar set in the charter | TH-14 | Hannah Brill | 2 | 2 | 4 | Low | 2 | 2 | 4 | Low | —
R-32 | The ISMS scope statement becomes inaccurate and Northgate is not notified within 30 days | TH-14 | Rahul Bhargava | 2 | 2 | 4 | Low | 2 | 2 | 4 | Low | —
R-33 | A restoration from backup reintroduces data that had been deleted | TH-08 | Devon Ashby | 2 | 3 | 6 | Low | 2 | 3 | 6 | Low | —
R-34 | An asset is missing from the inventory and is therefore outside every control applied to its class | TH-14 | Wes Delacroix | 3 | 2 | 6 | Low | 2 | 2 | 4 | Low | L 3 → 2
R-35 | Leave-type data reaches a report or export seen by a party who should not see it | TH-05 | Devon Ashby | 2 | 3 | 6 | Low | 2 | 3 | 6 | Low | —
R-36 | A CloudNimbus employee's own personal data is mishandled | TH-14 | Hannah Brill | 2 | 2 | 4 | Low | 2 | 2 | 4 | Low | —

## Band summary
Band Summary — baseline against the published forecast
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 03 · Illustrative Portfolio Sample
Band | Baseline | Forecast (36 entries) | Forecast at close (38 entries)
High | 7 | 0 | 0
Moderate | 17 | 14 | 16
Low | 12 | 22 | 22
TOTAL | 36 | 36 | 38

## Immovable
Entries forecast not to move, and why
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 03 · Illustrative Portfolio Sample
ID | Rating | Reason
R-19 | 2 × 5 = 10 | Immovable — the next likelihood step is 1, reserved for the not reasonably foreseeable, and the consequence has not changed
R-20 | 2 × 5 = 10 | Immovable — the next likelihood step is 1, reserved for the not reasonably foreseeable, and the consequence has not changed
R-24 | 2 × 4 = 8 | On the floor — a 2 × 4 stops at eight
R-26 | 2 × 3 = 6 | Already Low at likelihood 2; the only remaining step is the reserved 1
R-27 | 2 × 3 = 6 | Already Low at likelihood 2; the only remaining step is the reserved 1
R-28 | 2 × 2 = 4 | Already Low at likelihood 2; the only remaining step is the reserved 1
R-29 | 2 × 3 = 6 | Already Low at likelihood 2; the only remaining step is the reserved 1
R-31 | 2 × 2 = 4 | Already Low at likelihood 2; the only remaining step is the reserved 1
R-32 | 2 × 2 = 4 | Already Low at likelihood 2; the only remaining step is the reserved 1
R-33 | 2 × 3 = 6 | Already Low at likelihood 2; the only remaining step is the reserved 1
R-35 | 2 × 3 = 6 | Already Low at likelihood 2; the only remaining step is the reserved 1
R-36 | 2 × 2 = 4 | Already Low at likelihood 2; the only remaining step is the reserved 1