## Treatment plan
Risk Treatment Plan — TP-01 to TP-34
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 03 · Illustrative Portfolio Sample
ID | Risk | Treatment | Owner | Target date
TP-01 | R-01 | Tenant predicate enforced in a single shared data-access layer, with a build-time check that fails any query path constructed without it | Junia Okonkwo | 2026-06-12
TP-02 | R-01 | Multi-tenancy isolation testing commissioned as a named scope in the independent testing engagement | Karim Haddad | 2026-05-22
TP-03 | R-02 | Independent recalculation of engine output on a separate code path, with a reconciliation exception queue and a two-business-day clearance SLA | Grete Lindqvist | 2026-06-19
TP-04 | R-03 | Standing privileged access removed; time-bound just-in-time elevation against a recorded approval, with session recording | Wes Delacroix | 2026-06-05
TP-05 | R-05 | Residency assertion enforced on every export, log and backup path, failing the build where a path can carry an identifier out of region | Devon Ashby | 2026-06-12
TP-06 | R-05 | Telemetry pseudonymised at source so that nothing crossing a region boundary carries an identifier | Devon Ashby | 2026-06-26
TP-07 | R-06 | Heartbeat alerting on every scheduled retention and deletion job, so that absence of a success signal raises the alert | Devon Ashby | 2026-06-05
TP-08 | R-06 | Monthly retention reconciliation comparing records past their rule against records actually deleted | Devon Ashby | 2026-06-30
TP-09 | R-07 | Production-to-non-production data movement prevented at the account and network boundary, with a named, time-boxed, approved exception path | Junia Okonkwo | 2026-06-19
TP-10 | R-08 | Peer review enforced by branch protection in the repository rather than by team convention, closing ML-2 | Junia Okonkwo | 2026-05-15
TP-11 | R-09 | Access provisioning gated on a recorded manager approval — no approval record, no grant | Wes Delacroix | 2026-05-29
TP-12 | R-10 | Quarterly access review moved into the GRC platform with a system-generated completion record, closing ML-1 | Wes Delacroix | 2026-06-12
TP-13 | R-11 | Infrastructure defined as code with drift detection and policy checks that block public exposure of a data store | Wes Delacroix | 2026-06-26
TP-14 | R-12 | Dependency scanning in the build pipeline with remediation service levels by severity and a blocking gate at critical | Junia Okonkwo | 2026-06-05
TP-15 | R-13 | Phishing-resistant multi-factor authentication for all staff, with quarterly simulation and targeted follow-up | Karim Haddad | 2026-06-19
TP-16 | R-14 | CUEC-05 restated in onboarding and a pre-export variance report published to the customer admin console before each export | Ana-Sofia Cruz | 2026-06-26
TP-17 | R-15 | Backup residue disclosed in the deletion certificate, with the 65-day window stated to the customer rather than engineered away | Devon Ashby | 2026-06-12
TP-18 | R-16 | Vendor register rebuilt with independent classification flags and the test re-applied at each quarterly review, closing ML-3 | Tobias Lund | 2026-05-29
TP-19 | R-17 | Sub-processor engagement blocked until the O5 notice has been issued and the 30-day objection period recorded | Tobias Lund | 2026-06-05
TP-20 | R-18 | Availability architecture change removing the single-writer failover dependency; requires a customer-notified maintenance window | Wes Delacroix | 2026-07-25
TP-21 | R-21 | Audit logging coverage assessed against every data access path, gaps closed, and archive retention fixed for the full examination period | Karim Haddad | 2026-06-19
TP-22 | R-22 | Incident notification workflow with the 48-hour clock started at determination and tracked to issue under O4 | Karim Haddad | 2026-06-12
TP-23 | R-23 | Data subject request intake, routing and ten-business-day tracking under the Data Protection Officer, per O6 | Tobias Lund | 2026-06-19
TP-24 | R-25 | Evidence architecture documented end to end and a second named operator trained and exercised on it; completion verified by the risk owner, not by the item owner — see §7.1 | Rahul Bhargava | 2026-06-26
TP-25 | R-26 | Full-disk encryption and remote wipe enforced through MDM across all 231 endpoints, with local caching of customer data restricted | Wes Delacroix | 2026-05-29
TP-26 | R-27 | Offboarding revocation triggered from the HR system on the last working day, with same-day confirmation recorded | Hannah Brill | 2026-06-05
TP-27 | R-29 | Concentration and exit assessment across the eleven sub-processors, with a documented exit path for each | Tobias Lund | 2026-06-26
TP-28 | R-30 | Documentation currency brought into the clause 9.2 internal audit programme alongside control operation | Rahul Bhargava | 2026-09-30
TP-29 | R-31 | Awareness training assigned on hire and annually, with completion reported monthly against the 95% bar | Hannah Brill | 2026-06-12
TP-30 | R-32 | ISMS scope statement reviewed at each Trust Committee, with the O10 notification path named and owned | Rahul Bhargava | 2026-06-19
TP-31 | R-33 | Post-restoration deletion re-execution procedure, proven in the disaster recovery exercise under CAL-10 | Devon Ashby | 2026-08-19
TP-32 | R-34 | Asset inventory reconciled monthly against cloud and MDM sources of truth, with unmatched assets escalated | Wes Delacroix | 2026-06-26
TP-33 | R-35 | Leave type restricted in reporting and export to a controlled list, with no free text and no reason field | Devon Ashby | 2026-06-19
TP-34 | R-36 | Employee personal data brought under the same classification, retention and access rules as customer personal data | Hannah Brill | 2026-06-26

## Options
Treatment Options — clause 6.1.3 a)
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 03 · Illustrative Portfolio Sample
Option | Count | Which
Modify | 31 | All risks not listed below
Retain | 4 | R-19, R-20, R-24, R-28
Share | 1 | R-04 — transferred in part to Halcyon Identity through contractual service levels, disclosed to user entities as CSOC-14
Avoid | 0 | None. Avoidance means ceasing an activity, and CloudNimbus ceased none.
TOTAL | 36