## Findings
Penetration Test Findings — Ironwood Security Labs, 2026-05-04 to 2026-05-22
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 05 · Illustrative Portfolio Sample
ID | Finding | Stream | Severity | Status | Remediated | Retested
PT-01 | The reporting API's aggregate endpoint returned another tenant's aggregate compensation totals when a nested filter was supplied | TS-05 | Critical | Closed | 2026-05-29 | 2026-06-11
PT-02 | An authenticated user could retrieve another user's expense receipt within the same tenant by object identifier | TS-03 | High | Closed | 2026-06-08 | 2026-06-26
PT-03 | The reporting service's IAM role carried object-read permission on a bucket prefix wider than the service required | TS-02 | High | Closed | 2026-06-12 | 2026-06-26
PT-04 | The Android client accepted a session token supplied in a deep-link parameter | TS-04 | High | Closed | 2026-06-19 | 2026-06-26
PT-05 | A legacy marketing subdomain permitted a deprecated cipher suite | TS-01 | Medium | Closed | 2026-06-30 | 2026-07-24
PT-06 | Rate limiting on password reset was applied per session rather than per account | TS-03 | Medium | Closed | 2026-07-08 | 2026-07-24
PT-07 | Object-level logging was not enabled on 2 of the 168 in-scope storage buckets | TS-02 | Medium | Closed | 2026-06-24 | 2026-07-24
PT-08 | The admin console did not require re-authentication before a role-assignment change | TS-03 | Medium | Closed | 2026-07-15 | 2026-07-24
PT-09 | The iOS client cached API responses containing personal data in an unencrypted on-device store | TS-04 | Medium | Open — scheduled | Release 2026-08-14 | —
PT-10 | A security group on the analytics replica permitted ingress from the whole VPC range rather than from the reporting service | TS-02 | Medium | Closed | 2026-06-24 | 2026-07-24
PT-11 | Verbose server header disclosure on the public edge | TS-01 | Low | Closed | 2026-06-30 | 2026-07-24
PT-12 | Referrer policy header absent on the customer web application | TS-03 | Low | Closed | 2026-07-08 | 2026-07-24
PT-13 | An unused access key older than ninety days on a service account | TS-02 | Low | Closed | 2026-06-24 | 2026-07-24
PT-14 | The Android client did not pin the API certificate | TS-04 | Low | Open — scheduled | Release 2026-08-14 | —
PT-15 | Tenant identifiers are sequential integers, which assists enumeration | TS-05 | Low | Open — accepted | — | —
PT-16 | The session cookie did not carry the host prefix | TS-03 | Low | Closed | 2026-07-08 | 2026-07-24

## Streams
Test Streams — TS-01 to TS-05
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 05 · Illustrative Portfolio Sample
ID | Stream | Scope | Findings | Which
TS-01 | External network | Internet-facing surface across three regions | 2 | PT-05, PT-11
TS-02 | Internal and cloud configuration | The five in-system AWS accounts, assumed-breach from a compromised workload | 4 | PT-03, PT-07, PT-10, PT-13
TS-03 | Web application | Customer web application and tenant admin console, authenticated and unauthenticated | 5 | PT-02, PT-06, PT-08, PT-12, PT-16
TS-04 | Mobile application | iOS and Android clients, including on-device storage and transport | 3 | PT-04, PT-09, PT-14
TS-05 | Multi-tenancy isolation | Cross-tenant access attempts against every documented data path | 2 | PT-01, PT-15
| TOTAL |  | 16

## Status
Status at the 2026-07-31 vantage
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 05 · Illustrative Portfolio Sample
Status | Findings | Which | Note
Closed and retested | 13 | PT-01, PT-02, PT-03, PT-04, PT-05, PT-06, PT-07, PT-08, PT-10, PT-11, PT-12, PT-13, PT-16 | Remediated and independently retested. Every remediation date precedes its retest date.
Open — scheduled | 2 | PT-09, PT-14 | Both ride the 2026-08-14 mobile release rather than being shipped out of cycle — DEC-510.
Open — accepted | 1 | PT-15 | Sequential tenant identifiers. Enumeration is not authorisation; the isolation control is the predicate, not the opacity of the identifier. Revisited at the second test — ADR-0022.
TOTAL | 16 |  | 13 + 2 + 1 = 16