## Availability
Availability against SC-01 — re-derived per region from downtime minutes
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 06 · Illustrative Portfolio Sample
Month | Region | Days | Announced minutes excluded | Downtime (min) | Measured minutes | Availability | Allowance at 99.9% (min) | SC-01
July 2026 | us-east-1 | 31 | 4 | 9 | 44636 | 99.98% | 44.64 | Met
July 2026 | eu-central-1 | 31 | 0 | 0 | 44640 | 100.00% | 44.64 | Met
August 2026 | us-east-1 | 31 | 23 | 13 | 44617 | 99.97% | 44.64 | Met
August 2026 | eu-central-1 | 31 | 0 | 0 | 44640 | 100.00% | 44.64 | Met
September 2026 | us-east-1 | 30 | 0 | 71 | 43200 | 99.84% | 43.2 | NOT MET
September 2026 | eu-central-1 | 30 | 0 | 0 | 43200 | 100.00% | 43.2 | Met
Mean of the three us-east-1 months = 99.93%. SC-01 is a monthly commitment and the mean is not the test.
August's 171 excluded minutes are the CAL-10 exercise window, announced 2026-08-05 under the MSA exclusion that 02.12 v1.0 omitted and v1.1 states.
September: the commitment was met for the 41 customers served from eu-central-1 and missed for the 599 served from us-east-1.

## Incident timeline
INC-2026-031 — 2026-09-08, all times UTC
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 06 · Illustrative Portfolio Sample
Time | Event
14:22 | The writer instance of the core-us-east Aurora cluster stops accepting writes
14:22:47 | RDS initiates automated failover
14:23:34 | Failover complete at the data layer — 47 seconds, inside design
14:24 | CNB-C-068's synthetic clock-in fails twice consecutively and pages the on-call SRE — two minutes after onset
14:26 | First customer report — a tenant at a shift boundary in the US Central time zone
14:29 | The CNB-C-067 error-rate path corroborates: the write error rate crosses its threshold
14:31 | Severity-1 declared under CNB-C-071; Wes Delacroix named incident commander
14:47 | Break-glass elevation used to inspect connection state on the production cluster
14:52 | Cause identified
15:04 | Rolling restart of the 11 services on the core write path begins
15:05 | September's SC-01 allowance is exhausted
15:33 | Writes restored; last service healthy. Customer impact 71 minutes (14:22–15:33)
15:41 | Incident closed after the CNB-C-077 acceptance checks, confirmed by the incident commander and the on-call SRE

## Post-incident actions
Actions arising from the post-incident review of 2026-09-11
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 06 · Illustrative Portfolio Sample
ID | Action | Owner | Status at 2026-09-30
ACT-06-01 | Pool health check executes a write probe; max_lifetime set to 900 seconds | Junia Okonkwo | Deployed 2026-09-12
ACT-06-02 | CNB-C-096 amended — the synthetic probe performs a write, the read probe retained as a separate signal | Wes Delacroix | Deployed 2026-09-19
ACT-06-03 | Availability defined in writing as both a read and a write succeeding in the measured minute | Nathan Oyelaran | Recorded 2026-09-11
ACT-06-04 | A quarterly in-region failover game day added from Q4, distinct from CAL-10 | Wes Delacroix | Scheduled 2026-11-05, not performed
ACT-06-05 | Status page vocabulary revised — "degraded" was displayed and the write path was not degraded, it was down | Ana-Sofia Cruz | Deployed 2026-09-22

## DR exercise
CAL-10 disaster recovery exercise — 2026-08-19, us-east-1 to us-west-2
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 06 · Illustrative Portfolio Sample
ID | Finding | Severity | Status
DR-F1 | The runbook assumed a 60-second DNS TTL; the record is published at 300, adding roughly four minutes to observed customer recovery | Material | Closed 2026-09-02
DR-F2 | The runbook did not state in terms that eu-central-1 must not be failed over | Moderate | Closed 2026-08-28
DR-F3 | Aurora global-database promotion required a manual approval step absent from the runbook's critical path timing | Moderate | Closed 2026-09-11
DR-F4 | The status page notice was drafted live rather than from a template | Minor | Closed 2026-09-04
DR-F5 | Two service runbook links pointed at a retired wiki | Minor | Closed 2026-08-26
DR-F6 | Failback was not timed; it took place over the two following days unmeasured | Moderate | Open — scheduled against the Q4 game day, due 2026-11-30
Recovery time objective 4 hours, achieved 2 hours 51 minutes. Recovery point objective 15 minutes, achieved 4 minutes 12 seconds. Both inside SR-10. eu-central-1 was deliberately not failed over: O8 and SC-04 forbid it.