## September review
CAL-06 risk register review — 2026-09-29 · six reduction proposals, none accepted
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 06 · Illustrative Portfolio Sample
# | Proposal | Outcome | Reason | Tested upward?
P-1 | Reduce R-18 — an availability incident breaches the 99.9% monthly commitment — on the figures then in force: July and August both at 99.99% on the read-only probe | Declined | The proposal was raised on 2026-09-04 and the event occurred four days later. A likelihood forecast contradicted by an event that actually happened is a forecast that must not be honoured. The 2026-09-24 re-derivation later moved both months, to 99.98% and 99.97% — which strengthens the decline rather than weakening it: the proposal rested on a number the instrument was overstating. Held at 3 × 3 = 9 | Yes — one occurrence is consistent with likelihood 3 and does not reach 4. Held
P-2 | Reduce R-19 — disaster recovery fails the four-hour objective in a real event — on the exercise result | Declined | Two independent grounds: an exercise is not a real event, and the next likelihood step is 1, which is reserved for the not-reasonably-foreseeable. Held at 2 × 5 = 10 | Not engaged — the described event did not occur
P-3 | Reduce R-21 — audit and security logging is incomplete, so an event cannot be reconstructed | Declined | The June forensic search is the event R-21 describes, not evidence against it, and it concluded before 2026-06-22, when DEC-508 reviewed the retention gap it exposed — before the window opened. What remains is one reconstruction, and one event is not a period. Held at 3 × 3 = 9 | Yes — one occurrence is consistent with likelihood 3. Held
P-4 | Reduce R-30 — documented information becomes out of date and is relied on as current — from 3 × 2 = 6 to 2 × 2 = 4 | Declined | DR-F1 is the event R-30 describes — a runbook assuming a 60-second DNS TTL against a record published at 300, relied on during a live exercise. Held at 3 × 2 = 6 | Yes — DR-F1 and DR-F3 are two occurrences, short of the likelihood 4 anchor. Held, and recorded as the next candidate to rise
P-5 | Reduce R-04 — Halcyon Identity becomes unavailable — on nine months without an authentication outage | Declined | The absence of a supplier outage is not evidence about a supplier's controls, which CloudNimbus neither designs nor operates. The same refusal 03.07 made. Held at 4 × 4 = 16 | Not engaged — no occurrence
P-6 | Reduce R-14 — a customer does not perform CUEC-05 and a wrong export reaches their payroll provider — on the CUEC-05 outreach | Declined | A 64% response rate to a question nobody answered "no" to is not evidence about likelihood. Held at 4 × 3 = 12 | Not engaged — no occurrence

## Band arithmetic
The register position, re-derived from the outcomes above
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 06 · Illustrative Portfolio Sample
Band | Before the review | Movement | After the review
High | 7 | 1 | 8
Moderate | 18 | -1 | 17
Low | 12 | 0 | 12
Total | 37 | 0 | 37
Six reductions were proposed and none was accepted. The only movement was a rating going up.
R-08 moved from 4 x 3 = 12 to 5 x 3 = 15 on the likelihood-5 anchor: nine occurrences in ninety-two days.
Nobody proposed it. The review reached it by testing every entry whose described event had occurred.
A High residual may not be retained on the risk owner's authority: Elise Fontaine's retention decision is minuted.
P-3 was declined because the June forensic search is the event R-21 describes, not evidence against it.
No risk was closed and none was removed, at this or any prior review.
No new risk was admitted: R-18 already describes the September incident (ADR-0029).

## Entries in evidence
Register entries this phase produced evidence about
CloudNimbus, Inc. — SOC 2 Type II + ISO/IEC 27001:2022 Programme · Phase 06 · Illustrative Portfolio Sample
Entry | Rating at 2026-09-30 | Band | What the quarter showed
R-04 | 4 × 4 = 16 | High | Nine months without an authentication outage. Held: the absence of a supplier outage is not evidence about a supplier's controls
R-08 | 5 × 3 = 15 | High | MOVED UP, unproposed. Nine of 160 changes reached production without a code-owner review at merge, by the designed emergency path. Likelihood 5 is 'occurring now'. CEO retention decision minuted; CA-06-03 open
R-14 | 4 × 3 = 12 | Moderate | The CUEC-05 outreach returned 411 of 640. Held: a 64% response rate is not evidence about likelihood
R-18 | 3 × 3 = 9 | Moderate | The event occurred on 2026-09-08, four days after a reduction was proposed
R-19 | 2 × 5 = 10 | Moderate | The exercise met 2h51m against 4h. Held: an exercise is not a real event, and likelihood 1 is reserved
R-20 | 2 × 5 = 10 | Moderate | The exercise could not cover eu-central-1, which O8 forbids failing over. Immovable
R-21 | 3 × 3 = 9 | Moderate | Reduction declined. The June forensic search is the event R-21 describes, and it closed before the window opened; one reconstruction is not a period
R-30 | 3 × 2 = 6 | Low | Reduction to 2 x 2 = 4 proposed and declined: DR-F1 is the event R-30 describes, and DR-F3 is in the same family. The next candidate to rise